## Profile Tables
Effect of profiling work. Effect of Work Contours in MS Project.
Type of loading:- | Case 1. A task with 40 hours of work, set to fixed work, with 1 unit of resource.
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Flat | 8 | 8 | 8 | 8 | 8 | [5 empty] | 40
Back Loaded | 0.87 | 1.47 | 3 | 4 | 5.67 | 6.33 | 8 | 8 | 2.67 |  | 40.01
Front Loaded | 8 | 8 | 7 | 6 | 4.33 | 3.67 | 1.73 | 1 | 0.27 |  | 40
Double Peak | 2 | 4 | 8 | 4 | 2 | 2 | 4 | 8 | 4 | 2 | 40
Early Peak | 2 | 4 | 8 | 8 | 6 | 4 | 4 | 2 | 1.2 | 0.8 | 40
Late Peak | 0.8 | 1.2 | 2 | 4 | 4 | 6 | 8 | 8 | 4 | 2 | 40
Bell | 0.8 | 1.6 | 3.2 | 6.4 | 8 | 8 | 6.4 | 3.2 | 1.6 | 0.8 | 40
Turtle | 2.57 | 5.14 | 7.72 | 8 | 8 | 5.43 | 2.85 | 0.28 |  |  | 39.99
Type of loading:- | Case 2. A task with 40 hours of work, set to fixed duration, with 1 unit of resource.
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | [5 empty] | Total
Flat | 8 | 8 | 8 | 8 | 8 | [5 empty] | 40
Back Loaded | 1 | 3 | 5 | 7 | 8 | [5 empty] | 24
Front Loaded | 8 | 7 | 5 | 3 | 1 | [5 empty] | 24
Double Peak | 3 | 6 | 2 | 6 | 3 | [5 empty] | 20
Early Peak | 3 | 8 | 5 | 3 | 1 | [5 empty] | 20
Late Peak | 1 | 3 | 5 | 8 | 3 | [5 empty] | 20
Bell | 1.2 | 4.8 | 8 | 4.8 | 1.2 | [5 empty] | 20
Turtle | 3 | 7 | 8 | 7 | 3 | [5 empty] | 28
www.ablesim.com

## Fixed Work Bar Charts
Case 1. A task with 40 hours of work, set to fixed work, with 1 unit of resource.

## Fixed Duration Bar Charts
Case 2. A task with 40 hours of work, set to fixed duration, with 1 unit of resource.